## Decision Matrix-OLD (hidden)
|  | Highest Possible Score -------------> |  | 100 |  | 90 |  | 80 |  | 70 |  | 60 |  | 50 |  | 40 |  | 30 |  | 30 |  | 30 |  | 20 |  | 10 | TOP POSSIBLE SCORE: | 610
CRITERIA KEY
|  | WEIGHTING-------------------------> |  | 10 |  | 9 |  | 8 |  | 7 |  | 6 |  | 5 |  | 4 |  | 3 |  | 3 |  | 3 |  | 2 |  | 1
Score 100% Scale | Total Score | Title | 0 | Score | 0 | Score | 0 | Score | 0 | Score | 0 | Score | 0 | Score | 0 | Score | 0 | Score | 0 | Score | 0 | Score | 0 | Score | 0 | Score | Total Score |  | Weight | Criteria | Description
0% | 0 | [25 empty] | 0 |  | 10
0% | 0 | [25 empty] | 0 |  | 9
0% | 0 | [25 empty] | 0 |  | 8
0% | 0 | [25 empty] | 0 |  | 7
0% | 0 | [25 empty] | 0 |  | 6
0% | 0 | [25 empty] | 0 |  | 5
0% | 0 | [25 empty] | 0 |  | 4
0% | 0 | [25 empty] | 0 |  | 3
0% | 0 | [25 empty] | 0 |  | 3
0% | 0 | [25 empty] | 0 |  | 3
0% | 0 | [25 empty] | 0 |  | 2
0% | 0 | [25 empty] | 0 |  | 1
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0
0% | 0 | [25 empty] | 0

## Short Form Template
Project Name: | Santa Clara Permit Data
Project Objective: | Extract permit data from Santa Clara and Update daily
Project Description:
Brainstorm Ideas:
Resources: | Santa Clara Pemit site
Project Deadline:
Percent Complete: | #DIV/0!
Priority (80/20) | Duration | Category / Action Item* | Weight | Done | Person Responsible* | Comments
* | 1 | Understand Requirments | 18 | 0
* |  | Explore Interface | 8 |  | RM | https://onedrive.live.com/view.aspx?resid=B78BA86445BEEDF8!128&authkey=!AEAu8MLR9VyL4Vs
* |  | Understand PRD and convert into action items | 10 |  | RM
* |  | Understand code |  |  | RM
| 0 | Resources | 0 | 0
* |  | Santa Clara Data Headers |  |  | AW | Check Sheet in this document
* |  | Santa Clara data browser |  |  | AW | https://smartpermit.santaclaraca.gov:8443/apps/cap_sc/#/lookup
| 1 | Data to Extract - Overview | 70 | 0
* |  | Name | 10 |  |  | Name of the location
* |  | Permit # | 10 |  |  | Alpha Numeric unique id per permit
* |  | Address | 10 |  |  | Text Address of the street
* |  | Applicant Date | 10 |  |  | Date
* |  | Project Name | 10
* |  | Status | 10
* |  | Description | 10
* | 1 | Validate Extraction Done Right
|  | Geo Point |  |  |  | GPS coords, extracted from Google Maps based on text address
|  | Data to Extract - Activities | 80 | 0
* |  | Title | 10 |  |  | Activity title
* |  | Assigned | 10
* |  | Done By | 10
* |  | Status | 10
* |  | Date Requested | 10
* |  | Target Date | 10
* |  | Received Date | 10
|  | Activity ID | 10 |  |  | Extracted the ID to make sure we only add new activities
* | 0 | Validate Extraction Done Right |  |  |  | Done in previous step no time needed
| 4 | Geo Coding Addresses | 0 | 0 |  | Complicated, would leave till last step
* |  | Check options |  |  |  | Recommend G maps because I have experiene with it
* |  | How many addresses to geocode? |  |  |  | this will effect choice and pricing
* |  | How to geocode only new addresses on Upsert
* | 2 | Google Maps API |  |  |  | (5.00 USD per 1000)
* |  | Get Google Maps API |  |  |  | Needs CC, Create Google Account
| 2 | Explore querying the data after upsert and geocoding missing |  |  |  | Skip for now
| 3 | Elasticsearch | 113 | 77
* | 0 | Get Elasticsearch Link | 3 | 10
* | 0 | Index the data |  | 10
* | 1 | Create Index Schema |  | 10 |  | Handles Geo and Dates
* | 2 | Create UpSert Function |  |  |  | Handled by the bulk index function and activity id
|  | Historical Data | 90 | 20
|  | Jan | 10 | 5 |  | Data Downloaded, need to index
|  | Feb | 10 | 5 |  | Data Downloaded, need to index
|  | Mar | 10 | 5 |  | Data Downloaded, need to index
|  | April | 10 | 5 |  | Data Downloaded, need to index
|  | May | 10
|  | June | 10
|  | July | 10
|  | August | 10
|  | Sept | 10
| 4 | Kibana | 20 | 27
* | 0 | Get Kibana Link |  | 10 | AW | https://search-county-records-mbz3w42c3ehmvsjcfb4tb2orly.us-east-1.es.amazonaws.com/_plugin/kibana/app/kibana#/discover?_g=()
* | 0 | Create Excel Sheet of data and send
| 0 | Create Mockup Dashboard in Excel |  |  | AW
* | 4 | Create Visualizations | 10 | 7 |  | Rough Estimate, depends on what are the viz
| 0 | Kibana Viusalizations | 10 | 10
map that shows all active projects with a filter for description
| 3 | Lambda | 10 | 10
| 2 | Create package and test |  |  | RM
| 0 | Get Access to AWS | 10 | 10 | AW
| 1 | Setup Cloud watch to run daily |  |  | RM | Cloudwatch trigger Rate daily??
Test Setup
Change to date to today
Combining Datasets
Join by date
Join by status
Error Handling
For geocoding
For talking to data
|  | Logging |  |  |  | Extra

## Santa Clara Data
County | Overview Tab | [6 empty] | Activities Tab
Santa Clara | Name | Permit # | Address | Applicant Date | Project Name | Status | Description | Title | Assigned | Done By | Status | Date Requested | Target Date | Received
Title
Assigned
Done By
Status
Date Requested
Target Date
Received